## Request for change
Request for Change (RFC)
Installation of Qualys and CrowdStrike for Enhanced Cybersecurity
Configuration Date: 13 June 2025
Geton Technology Co.,Ltd

## Preparation Task
1. Title: Installation of Qualys and CrowdStrike for Enhanced Cybersecurity
2. Objective and Reason for Change: To install Qualys and CrowdStrike to enhance system security and threat protection.
3. Description of Change and related work (Configuration procedure or Step by Step):
Preparation
No. | Pre-task | Owner | Time Start | Time Stop | Downtime | Configuration Detail
1.1 | Take the VM snapshot | GetON | 13/06/2025 10:00 | 13/06/2025 10:10 | No | 1. Access to my sql
2. Run command : mysql -u root -p
3. Check databases in mysql

## Configuration Step
1. Title: Installation of Qualys and CrowdStrike for Enhanced Cybersecurity
2. Objective and Reason for Change: To install Qualys and CrowdStrike to enhance system security and threat protection.
3. Description of Change and related work (Configuration procedure or Step by Step):
Configuration Procedure : Pivotal Container Service Migrate to Nutanix Karbon
No. | Pre-task | Owner | Estimate time | Time Start | Time Stop | Downtime | Configuration Detail
2.1 | Install Qualys On VM | GetOn | 20 mins | 13/06/2025 11:00 | 13/06/2025 11:20 | No | 1. คำสั่งติดตั้ง Qualys
2.Run command : sudo dpkg --install QualysCloudAgent.deb
3. กำหนดค่า Agent
4. Run command : sudo /usr/local/qualys/cloud-agent/bin/qualys-cloud-agent.sh ActivationId=5180de4d-83a3-45ec-825f-8562bd3fef7c CustomerId=b77372be-ce61-416f-83f5-de0405ab1bf1 ServerUri=https://qagpublic.qg1.apps.qualys.com/CloudAgent/
5. ตรวจสอบสถานะ
6. Run command : sudo systemctl status qualys-cloud-agent
3.1 | Install Crowdstrike On VM | GetOn | 20 mins | 13/06/2025 11:20 | 13/06/2025 11:40 | No | 1.Run the installer, substituting <installer_filename> with your installer's file name
2.Run command : sudo dpkg -i <falcon-sensor_7.25.0-17804_amd64.deb>
3.Set your Falcon Customer ID (CID):
4.Run command : sudo /opt/CrowdStrike/falconctl -s --cid=<B2D802B0C8884D48974027FBA64B9CB9-A0>
5.เริ่มและเปิดการทำงานอัตโนมัติ
6.Run command : sudo systemctl start falcon-sensor
7.Run command : sudo systemctl enable falcon-sensor
8.ตรวจสอบสถานะ agent
9. Run command : sudo systemctl status falcon-sensor

## Roll Back Plan
1. Title: Installation of Qualys and CrowdStrike for Enhanced Cybersecurity
2. Objective and Reason for Change: To install Qualys and CrowdStrike to enhance system security and threat protection.
3. Description of Change and related work (Configuration procedure or Step by Step):
Roll Back Plan
No. | Pre-task | Owner | Time Start | Time Stop | Configuration Detail
3.1 | Restore the VM snapshot. | TLT | 13/06/2025 11:40 | 13/06/2025 12:00