## Request for change
Request for Change (RFC)
Installation of ABC
Configuration Date: 18 August 2025
Geton Technology Co.,Ltd

## Preparation Task
1. Title: Installation of ABC
2. Objective and Reason for Change: To install ABC to enhance system security.
3. Description of Change and related work (Configuration procedure or Step by Step):
Preparation
No. | Pre-task | Owner | Time Start | Time Stop | Downtime | Configuration Detail
1.1 | Pre-task1 | GetON | 18/08/2025 10:00 | 18/08/2025 10:10 | No | 1. Access
2. Run command
3. Check databases

## Configuration Step
1. Title: Installation of ABC
2. Objective and Reason for Change: To install ABC to enhance system security.
3. Description of Change and related work (Configuration procedure or Step by Step):
Configuration Procedure : Pivotal Container Service Migrate to Nutanix Karbon
No. | Pre-task | Owner | Estimate time | Time Start | Time Stop | Downtime | Configuration Detail
2.1 | Pre-task2 | GetOn | 20 mins | 18/08/2025 11:00 | 18/08/2025 11:20 | No | 1. คำสั่งติดตั้ง
2.Run command
3. กำหนดค่า Agent
2.Run command
5. ตรวจสอบสถานะ
2.Run command
3.1 | Pre-task3 | GetOn | 20 mins | 18/08/2025 11:20 | 18/08/2025 11:40 | No | 1.Run the installer
2.Run command
3.Set Customer ID (CID):
2.Run command
5.เริ่มและเปิดการทำงานอัตโนมัติ
2.Run command
2.Run command
8.ตรวจสอบสถานะ agent
2.Run command

## Roll Back Plan
1. Title: Installation of ABC
2. Objective and Reason for Change: To install ABC to enhance system security.
3. Description of Change and related work (Configuration procedure or Step by Step):
Roll Back Plan
No. | Pre-task | Owner | Time Start | Time Stop | Configuration Detail
3.1 | Pre-task4 | TLT | 13/06/2025 11:40 | 13/06/2025 12:00